Company Initialization Outline - ASP/DeltaV US Branch

Jose Maria Barbeito

25/1/26

### PHASE 1 — U.S. Legal & Business Formation

- Choose the U.S. Legal Entity

  - LLC

    - File taxes as S-corp until restructuring is needed

    - File LLC Registration with NC SOS

- File Articles of Organization/Incorporation with NC

  - Draft Operating Agreement / Bylaws

    - Get NC attorney to look over and certify proper structure

  - Obtain an EIN (Employer Identification Number) from the IRS (LINK) ✅

- Register for Federal & State Taxes

  - IRS EIN (see above) ✅

  - State tax registration (LINK)

    - (income tax, sales tax if distributing)

  - Import/export tax IDs

    - CBP Form 5106

    - More research needed for import/export laws

- Open Corporate Bank & Financial Accounts

  - Multi-currency accounts if needed

### PHASE 2 — IMPORTATION & DISTRIBUTION Setup

- U.S. Import Compliance

  - ITAR/DECCS for Import/Export License

    - Submit Application

    - Pay 3000 fee

    - Get approval

  - Ballistic vests are dual-use protective gear, potentially regulated under:

    - U.S. Customs and Border Protection (CBP)

    - Bureau of Industry and Security (BIS) — export control (EAR)

    - International Traffic in Arms Regulations (ITAR), if considered defense articles (rare for soft armor but possible for certain helmets)

  - Classify products under HTSUS (Harmonized Tariff Schedule) to determine duty rates (Website LINK) (Webinar Link) (User guide link)

  - Identify ECCN if controlled (typically EAR99 for non-military) (Link)

  - Work with a licensed customs broker

  - Ensure proper country of origin marking on products

  - DECCS Registration for license (LINK)

- Documentation Required:

  - Commercial invoice

  - Packing list

  - Bill of lading/Air waybill (Explanation)

    - We need bill of lading most likely - shipped by sea

  - Importer Security Filing (ISF)

  - HTS code & duty payments

- Contracts with Argentine Manufacturer (DeltaV/ASP)

Need a Distribution Agreement/contracts that clearly define:

- Exclusive vs Non-Exclusive territory rights

- Pricing and MOQ

- Intellectual Property ownership/usage

- Warranty & indemnification

- Product quality standards

- Logistics responsibilities

- Labeling requirements for U.S. market

Key Clauses:

- Clear delineation of who owns marketing rights in U.S.

- Allocations/lead time guarantees

- Insurance (transport, liability)

### PHASE 3 — NIJ Certification for U.S. Distribution

- Contact an NIJ-CTP

- Contact an NIJ-accredited testing laboratory

- Submit samples from Argentine production

- Receive test results and certification paperwork

### PHASE 4 — U.S. Manufacturing & New NIJ Certification

- Prepare for Manufacturing Setup

  - Critical decisions:

    - Location (state incentives, labor pool)

    - Facility size and workflow

    - Machinery and tooling

    - Skilled labor for sewing/composites

- Regulatory Requirements:

  - OSHA compliance

  - Environmental permits (if resin/fiber cutting)

  - Local zoning

- Design/Manufacturing Documentation for NIJ

  - Bill of Materials per model

  - Manufacturing work instructions

  - Quality assurance checkpoints

  - Traceability system for materials (lot/heat numbers)

- Obtain New NIJ Certification for U.S.-Made Products

### PHASE 5 — Distribution & Sales Infrastructure

- Warehouse & Logistics

  - Consider third-party logistics (3PL)

  - Choose fulfillment for ecommerce + bulk orders

- Sales Channels

  - Government (law enforcement, fire rescue)

  - Private security

  - Direct-to-consumer

  - Distributors

- For Government Sales:

  - Register in SAM.gov

  - Understand FAR clauses if selling to federal agencies

### PHASE 6 — Liability and Risk Management

- Product Liability Insurance

  - Critical given inherent safety use cases

  - Coverage for bodily injury claims

  - Recall protection

  - Legal expense coverage

- Indemnification & Warrantie

  - Contracts must protect you from:

  - Manufacturer defects

  - Misuse claims

  - Non-compliant products

### PERMITS & KEY COMPLIANCE CHECKPOINTS (Summary)

| Area | Requirement | Responsible |
| --- | --- | --- |
| Company Formation | State filing + EIN | You/Attorney |
| Import | CBP compliance, customs broker | You/3PL |
| Product Standard | NIJ certification | You + Lab |
| Sales Tax | State registration | You/CPA |
| OSHA | Manufacturing safety | You |
| Insurance | Liability policy | Broker |
| Government Sales | SAM.gov | You |

### TIMELINE ESTIMATE

- Entity & bank setup — 1–2 weeks

- Import compliance & contracts — 3–6 weeks

- Initial NIJ certification on imported products — 8–12 weeks

- U.S. manufacturing setup — 3–9 months

- NIJ certification for U.S.-made — additional 8–12 weeks

RECOMMENDED PROFESSIONAL SUPPORT

| Advisor | Why |
| --- | --- |
| Corporate attorney (U.S.) | Entity formation, contracts |
| Customs broker | Import compliance |
| CPA/Tax advisor | State sales tax, income tax |
| NIJ testing consultant | Prepare submission packages |
| Insurance broker | Liability & product risk |
| 3PL partner | Warehousing & fulfillment |